## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations required for doing project
|  | 2 | LLM for Contract analysis
|  | 3 | Clause Identification and Risk Analysis Engine
|  | 4 | Update tracking and Contract Modification
Note on F1: ====== ID#AAABv6zxcdw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | DDd
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Foundations Required for doing Project | Nov 10th | Nov 24th | Chinthala Keerthi | understood all the fundamentals required for the project | Done |  | introduction session | installation of python and jupyter | Python Keywords,Naming convention and rules for identifiers | understanding Variables and how to fill on the agile sheet | understanding Multi Variables and Datatypes | Revising previous session topics | Practiced all topics covered in previous session | learnt about range, Mutable and immutable data, 'if' flow control | Flow controls and functions in python | Functions with return keyword, arguments and types | learnt about modules and Keywords | OOPS in python | Constructors, and Instance Variables in python | Revision
In
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Chinthala Keerthi | Understood about Project, executed some demo codes. | Done |  | Project Discussion | Presentation about Project understanding | how to createVirtual Environment in detail | introduction to Tech Tools required for this project | Presentation about Project | Creating virtual environment | Revised previous comcepts | overview about prompt engineering | Gen AI and AI | learnt about LLM fundamentals and API key generation | Demo codes are Explained and execute | learnt about Packages and workflow of milestone-2 | practiced demo codes from beginning of the process | revised about python
3 |  | Clause Identification and Risk analysis engine | Dec 10th | Dec 24th | Chinthala Keerthi | Understood about clause extraction and risk analysis | Done |  | Overview about workflow and Project Structure | Overview about workflow and Project Structure | learnt about Text extraction and overlapping concept | cleaning and chunking clauses | learnt about Clause extraction and storing them | Revised extraction and chunking topics | Revised this week topics | Discussed on completion and submission of assignments & cleared some of ours queries | discussed on risk analysis engine and introduction to hands on implementation | Understood about run.py and pipeline.py codes and introduction about regulatory update tracking | practiced on milestones | Regulatory update tracking | worked on assignment tasks | worked on assignment tasks
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Chinthala Keerthi | Update tracking and contract modification | Done |  | Practiced assignment | assignment presentation | Learnt about Regulatory update Tracking theoretically | Executed demo 1 code and assignment presentation | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | revised about previous topics | practiced milestone-3 demo codes | Discussed about Contract Modification and Amendent Engine | Revised on milestone 3 topics and codes | Implemented of Milestone 3 codes | Practised Milestone 3 demo codes | discussed on feedparser and alternations for Milestone 3 codes limitations | learnt about Slack integration | Practiced on slack integration
Note on D2: ====== ID#AAABv5noruQ Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABv6zxceE Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABv6zxceM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABv6zxceY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABv6zxceU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABv6zxceA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABv5noruA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABv5noruI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABv6zxcec Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABv6zxceI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABv6zxcd4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABv6zxcd8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABv5noruM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABv5noruU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABv6zxceQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABv5noruE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABv6zxcd0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7